## Sheet1
Project Planner | [5 empty] | Hours spent per month
Task | Hours Estimated for Task | Deadline (date) | Hours Spent (calculated) | (Over)/ Under budget | Cumulative Hours | Jun '20 | Jul '20 | Aug '20 | Sep '20 | Oct '20 | Nov '20 | Dec '20 | Jan '21 | Feb '21 | Mar '21 | Apr '21 | May '21 | Notes
Create Website | 1 | 2020-06-08 | 3 | -2 | 3 | 3 | [11 empty] | Website completed, will continue to evolve throughout project.
Create Parameters for Every Game | 3 | 2020-07-01 | 3 | 0 | 6 | 3 | [11 empty] | Created parameters for all the games which could change as the project progresses
Create Menus and Navigation | 5 | 2020-08-01 | 5 | 0 | 11 |  | 5 | [10 empty] | Made menu system for the application
Code 1st game | 5 | 2020-08-29 | 5 | 0 | 16 |  |  | 5 | [9 empty] | 1st game completed for now, could change a bit later
Code 2nd game | 5 | 2020-09-30 | 5 | 0 | 21 | [5 empty] | 5 | [6 empty] | 2nd game completed for now, could change a bit later
Code 3rd game | 5 | 2020-10-31 | 5 | 0 | 26 | [5 empty] | 5 | [6 empty] | 3rd game completed for now, could change a bit later
Code 4th game | 5 | 2020-11-30 | 5 | 0 | 31 | [6 empty] | 5 | [5 empty] | 4th game completed for now, could change a bit later
Code 5th game | 5 | 2020-12-31 | 5 | 0 | 36 | [6 empty] | 5 | [5 empty] | 5th game completed for now, could change a bit later
Code 6th game | 5 | 2021-01-31 | 8 | -3 | 44 | [7 empty] | 4 | 4 |  |  |  | 6th game completed for now, could change a bit later
Code 7th game | 5 | 2021-02-28 | 4 | 1 | 48 | [9 empty] | 4 |  |  | 7th game completed for now, could change a bit later
Code 8th game | 5 | 2021-03-30 | 3 | 2 | 51 | [9 empty] | 3 |  |  | 8th game completed for now, could change a bit later
Finalize Application Details | 10 | 2020-05-01 | 2 | 8 | 53 | [10 empty] | 2 |  | Finishing touches added to application
Testing | 10 | 2020-05-29 | 2 | 8 | 55 | [11 empty] | 2 | Fellows Fair - unable to get to lower school due to COVID
TOTALS | 69 |  | 55 | 14 | 55